| Theme/ Topic: SUSTAINABILITY CURRICULUM Target/s: (numerical - if applicable) Long Term Goal: Increase students’ understanding about caring for the environment. 2022/23 Goal: Track and scope and sequence sustainability units in the R-12 curriculum with the aim of encouraging our students to “be in nature”. Enhance staff confidence to embed sustainability units into the curriculum |  |  |  |
| --- | --- | --- | --- |
| Strategies to achieve action | Responsibility | Timeframe | Completed |
| Establish a curriculum working party | Curriculum leaders, staff | Term 1 |  |
| Research existing sustainability curriculum framework documents | Working party | Term 1 |  |
| Complete an assessment of where the sustainability goals around energy, water, waste, biodiversity, health and wellbeing are currently being taught. Document the findings. | Working party , Curriculum leaders | Term 1 |  |
| Consult with internal resources and external sustainability bodies to gather information about how to further embed care for environment into the curriculum. | Working party , Curriculum leaders | Term 2 |  |
| Work with curriculum leaders to assist in embedding sustainability units and resources into the curriculum. | Working party , Curriculum leaders | Term 3 |  |
| Work with staff to consciously embed sustainability units and resources into the curriculum | Curriculum working party and curriculum leaders | Term 3 & 4 |  |
| Work with staff to link curriculum with external community projects (i.e., Citizen Science, Landcare). | Curriculum working party and curriculum leaders, staff. | Term 3 & 4 |  |

| Evaluation (How will we know if we have succeeded?) | Curriculum working party report to Environment Committee changes to curriculum annually. Track changes to sustainability curriculum audit on an annual basis. Unit plans of sustainability units describe resources (internal/external, physical/human). |
| --- | --- |